## Bug Report
OMFYS Technologies India Pvt.Ltd
Bug Report Sheet
Project: | MindsConnect - Human Capital Management (MC_HCM) | [7 empty] | Open | 9 | Fixed | 0
Updated on : | 20-Aug-2026 | [7 empty] | Reopen | 0 | Closed | 0
[9 empty] | Rejected | 0 | Hold | 0
Sr.No | Issue Raised By | Date | Module Name | Sub Module | Form name | Issues | Navigation steps to Reproduce | Status | Priority | Assigned To | Tester Comments | Developer Comments | Completion Date | Screenshot
1 | Parth Divekar | 21-Aug-2026 | Confirmation and Probation | All Requests | Request Table | Vertical scrolling is blocked when the mouse pointer is hovered over the Request Table/Card | Confirmation and Probation -> All Requests -> Request Table | Open | Medium | Mitasha Puri | Bug is Applicable for all roles in the All requests Tab, also after pagination number is changed the scrolling is not working |  |  | screenshots
2 | Parth Divekar | 22-Aug-2026 | Onboarding Approval | View Button | Approve | Validation message is partially hidden when submitting duplicate Corporate Email after scrolling | Login as Admin -> Onboarding Approval -> View Candidate (James Clear)-> approve -> Reporting Structure ->Approve | Open | Low | Mitasha Puri |  |  |  | screenshots
3 | Parth Divekar | 24-Aug-2026 | Conformation and Probation | Dashboard | Probation Period | For the current Trainee employee, the Probation Period start date is incorrectly displayed before the Date of Joining, even though the Training Period is still ongoing. And hasn't approved yet. | login as James Clear ->Conformation and Probation -> Dashboard -> Probation Period | Open | Medium | Charuli Shirsath | password for James Clear - JSkMcq7gK4 |  |  | screenshots
4 | Parth Divekar | 24-Aug-2026 | Reset Password | Reset Password | Reset Password | The Reset Password button is unresponsive when the system displays the “Failed to sync with old system” error during password reset. | Reset Password | Open | High | Charuli Shirsath |  |  |  | screenshots
5 | Parth Divekar | 25-Aug-2026 | Conformation and Probation | All Requests | View Action | After approving the Trainee-to-Probation request, the Employee Summary displays the Probation Period instead of the Training Period, while Training Days still shows 5. | Login as admin ->Conformation and Probation -> All requests -> Candidate name (James Clear) -> View ->Training Period | Open | High | Charuli Shirsath |  |  |  | screenshots
6 | Parth Divekar | 25-Aug-2026 | Conformation and Probation | Dashboard | Probation Period Field | After HR approves the candidate for Probation completion, the candidate is unable to view the Probation Period after logging in. | Conformation and Probation -> Login as Steve Rogers (OMI-3047)-> dashboard -> Probation Period Field | Open | High | Charuli Shirsath | password for Steve Rogers - qcjeTNrtX8 |  |  | screenshots
7 | Parth Divekar | 25-Aug-2026 | Conformation and Probation | All Requests and Audit Log | All Requests and Audit Log | For candidate name Steve Rogers, 4 approval levels were configured, but the Audit Log incorrectly displays 5 approval levels for the request. | login as Admin -> All requests -> candidate (Steve Rogers-OMI-3047)->view, then see for that candidate in the audit logs | Open | Medium | Charuli Shirsath | passsword for steve -> qcjeTNrtX8 |  |  | screenshots
8 | Parth Divekar | 25-Aug-2026 | Conformation and Probation | Letter Generated | Letter Generated | When an experienced candidate is converted from Probation to Confirmation after approval, the generated letter shows the Confirmation Start Date as the scheduler trigger date instead of the actual confirmation date. | login as OMI-3045-> Conformation and Probation -> My documents | Open | Medium | Charuli Shirsath | password for candidate-> cX18ecy0cm |  |  | screenshots
9 | Parth Divekar | 25-Aug-2026 | Confirmation and Probation | Letter Generated | Letter Generated | After the candidate completes the Training Period and the HR approves the request, the generated letter displays the Training Start Date (24-Aug-2026) under the incorrect label Probation Start Date. The letter should display the date with the correct label corresponding to the candidate's Training Period. | Confirmation and Probation -> Letter Generated | Open | Medium | Charuli Shirsath | password for login -> cX18ecy0cm |  |  | screenshots

## Sheet1 (hidden)
Open | Accepted
Reopen | Rejected
Fixed | Hold
Rejected
Closed
Hold | High
Medium
Low
Blocker

## Bug_4041_Screenshots
Bug ID: 4041
Screenshot : 1

## Bug_4061_Screenshots
Bug ID: 4061
Screenshot : 1
Screenshot : 2

## Bug_4081_Screenshots
Bug ID: 4081
Screenshot : 1

## Bug_4082_Screenshots
Bug ID: 4082
Screenshot : 1

## Bug_4101_Screenshots
Bug ID: 4101
Screenshot : 1

## Bug_4102_Screenshots
Bug ID: 4102
Screenshot : 1
Screenshot : 2

## Bug_4103_Screenshots
Bug ID: 4103
Screenshot : 1
Screenshot : 2
Screenshot : 3
Screenshot : 4

## Bug_4104_Screenshots
Bug ID: 4104
Screenshot : 1
Screenshot : 2

## Bug_4105_Screenshots
Bug ID: 4105
Screenshot : 1
Screenshot : 2
Screenshot : 3